## Sheet1
| Weeks | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
Task deadlines
Significant events |  | Summer Holiday | [14 empty] | Winter Holiday |  |  | Exam Period
Project Management WP0
Define initial work packages
Update work packages
Beurocracy WP4
Request access to 3d scanners
Request access to CMM
Request Subsonic Tunnel access
Testing WP1.1
Design test article
Manufacture 'dumb' test article
Manufacture 'old' test article
Manufacture 'new' article
Measure Test articles
Design tunnel mounts
Manufacture tunnel mount
Perform tunnel tests
Deliverables WP3
Skill development and project plan
Abstract
Draft paper
Non technical summary
Seminar presentation
Education WP5
Back Propogation
ADAM's
B-Splines
Software
Enviroment Setup
Implementation