## Tabelle1
Work Package: | Participants:
WP0 | Me
Objectives: | Start: Duration : End
Project management
Inputs:
Tasks:
Outputs:
Work Package: Testing | Participants: | Work Package: Development | Participants: | Work Package: Deliverables | Participants: | Work Package: Beurocracy | Participants: | Work Package: Education | Participants: | Work Package: Software | Participants:
WP1.1 | Me | WP2.0 | Me | WP3 | Me | WP4.1: | Me | WP 5 | Me | WP 5 | Me | Work Package: | Participants:
Objectives: | Start: | Objectives: | Start: Duration : End | Objectives: | Start: Duration : End | Objectives: | Start: Duration : End | Objectives: | Start: Duration : End | Objectives: | Start: Duration : End
Design Test Article |  | Manufacture Test Articles using 'Raw' path |  | Abstract |  | What resrouces can I get access to, CMS, 3d scanning? |  | Increase knowledge base |  | Developing softare |  | Objectives: | Start:
Inputs: |  | Inputs: |  | Inputs: |  | Inputs: |  | Inputs: |  | Inputs:
|  |  |  | WP 5 |  | None |  | None |  | WP5.1 WP5.2, WP 5.3 |  | Inputs:
Tasks: |  | Tasks: |  | Tasks: |  | Tasks: |  | Tasks: |  | Tasks:
Design Test article, consider what will best demonstrate improvement |  |  |  | Abstract |  | Go and speak to the 3D print lab about getting access to there 3D scanner. Need to figure out how who to contact to get use of the CMM. Speak to robert hyneman, scan qr code on 3d print lab for scanning |  | There is a signifciat I ndebendent study aspect to this research project it is important to lay this ground work early in the project asnot to delay later stages |  | Pretty nebulious, can be more specific once further work has been completed |  | Tasks:
Outputs: |  | Outputs: |  | Outputs: |  | Outputs: |  | Outputs: |  | Outputs:
A 2d profile or 4d volume for the test article that is suitable for manufacturing and that will accuratly capture machine behaviours | [7 empty] | Intangable |  |  |  | Outputs:
Work Package: | Participants: | Work Package: Development | Participants: | Work Package: Deliverables | Participants: | Work Package: Beurocracy | Participants: | Sub Package: Education | Participants:
WP1.2 | Me | WP2.1 | Me | WP3.1 | Me | WP4.2: | Me | WP 5.1 | Me
3 | Start: | Objectives: | Start: Duration : End | Objectives: | Start: Duration : End | Objectives: | Start: Duration : End | Objectives: | Start: Duration : End
Manfucature Test Articles |  | Manufacture Test Articles using old correction path |  | Draft Paper |  | Book Wind tunnel time |  | ADAMS
Inputs: |  | Inputs: |  | Inputs: |  | Inputs: |  | Inputs:
WP 1.1 |  |  |  | Everything |  | None |  | None
Tasks: |  | Tasks: |  | Tasks: |  | Tasks: |  | Tasks:
Manufacture, old, new and reference Airfoils |  |  |  | TBTb |  | Already spoken with oz, but hes been diffiecult to contact since, get a test date with the wind tunnels which leaves enough time for devlopment and manufacturing. |  | Learn about ADAMS, play with it a bit, see if it is suitable, research its performance and thoeretical impletnatation
Outputs: |  | Outputs: |  | Outputs: |  | Outputs: |  | Outputs:
A set of 3 airfoils that can be used for windtunnel testing | [5 empty] | Time and Date for testing |  | Intangable
Work Package: | Participants: | Work Package: Development | Participants: | Work Package: Deliverables | Participants: |  |  | Sub Package: Education | Participants:
WP1.3 | Me | WP2.1 | Me | WP3.2 | Me |  |  | WP 5.1 | Me
Objectives: | Start: | Objectives: | Start: Duration : End | Objectives: | Start: Duration : End |  |  | Objectives: | Start: Duration : End
Measure Manufactured Test Article |  | Get CMS measurments, compare and contrast |  | Non technical summary |  |  |  | Back Propogation
Inputs: |  | Inputs: |  | Inputs: |  |  |  | Inputs:
Test articles |  | WP4.1, WP 1.4, WP 2.0, WP 2.1 |  | Unkn own at this time
Tasks: |  | Tasks: |  | Tasks: |  |  |  | Tasks:
Measure test article surface using enther a CMM or 3d scanner, compare the surfaces of the 3 articles to the ground truth. |  | Measure the manufactured foils using the Universities 3d scanners, will need to contact the 3d print lab for this service |  | Write a non techical summary of work completed, should be suitable for a lay audience. This can be of any form, a tik tok, a you tube video, anything. It should be engaging and approachable. |  |  |  | Learn about back progation, practice with it a bit see if it would be suitable
Outputs: |  | Outputs: |  | Outputs: |  |  |  | Outputs:
|  |  |  | A piece of media approachable by all |  |  |  | Intangable
Work Package: | Participants: |  |  | Work Package: Deliverables | Participants: |  |  | Sub Package: Education | Participants:
WP1.4 | Me |  |  | WP3.3 | Me |  |  | WP 5.1 | Me
Objectives: | Start: |  |  | Objectives: | Start: Duration : End |  |  | Objectives: | Start: Duration : End
Perform Wind tunnel testing |  |  |  | Seminar Presentation |  |  |  | B-Splines
Inputs: |  |  |  | Inputs: |  |  |  | Inputs:
WP 1.2 |  |  |  | Everything
Tasks: |  |  |  | Tasks: |  |  |  | Tasks:
Test, tst artucles in subsonic project tunnel, testing at a variety of reynolds numbers and angles of attack, comparing the results to the theoretical model and ground truth model. |  |  |  | A presentation to a resonable adience about work completed, meotivation and results
Outputs: |  |  |  | Outputs: |  |  |  | Outputs:
Intangable
Work Package: | Participants:
WP1.5 | Me
Objectives: | Start:
Analyse consequences
Inputs:
Tasks:
the results of the windtunnel experiment will allow us to understand how the surface quality effect aerodynamic performance and enform us of the relative importance of the foil geometry.
Outputs: